## Sheet1
TWIC Project Plan
TASKS | Start date | End date | Duration | Resource/s | Student Name | Completed | Comments
TEAM MEETINGS
1 | 21/09/20 | 21/09/20 | 1 day | Microsoft Teams | ALL | Yes | Inital meeting to decide on project format and roles within the team
Minutes | 21/09/20 | 21/09/20 | 1 day | Microsoft Word Notepad | Robert | Yes | Minutes of first meeting
2 | 23/09/20 | 2020-09-23 | 1 day | MS Teams, MS Word, MS Excell | All | Yes | Follow up meeting to finalise Project Plan and research goals before Assesment 1 hand in
Minutes | 2020-09-23 | 2020-09-23 | 1 day | MS Word | Blu | Yes | Minutes of meeting 2
3 | 2020-10-05 | 2020-10-05 | 1 Day | MS Teams, MS Word, MS Excell, Google Suite | All | Yes | Meeting to discuss assesment 1, begin assessment 2
Minutes | 2020-10-05 | 2020-10-05 | 1 Day | MS Word | Blu | Yes | Minutes of meeting 3
ANALYSIS
Evaluate Case Study | 21/9/20 | 21/09/20 | 1 day | Microsoft Teams | ALL | Yes | Identified 4 areas to investigate, one for each team member
Project Proposal | 21/09/20 | 21/09/20 | 1 day | MS Teams, MS Word | ALL | Yes | Identify what we hope to achieve in project
Project Format | 21/09/20 | 21/09/20 | 1 day |  | ALL | Yes | Identify how we structure our findings
RESEARCH
Security Issues on Website | [5 empty] | Ongoing
Identify main issues | 2020-09-21 | 2020-09-21 | 1 day | MS Teams, MS Word | Robert | Yes | Identified issues during initial meeting
Propose realistic solutions | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Robert | Ongoing
Research providing positives and negatives for each | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Robert | Ongoing
Report findings | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Robert | Ongoing
Selling to 3rd parties |  |  |  | internet, google suite, MS Teams |  | Ongoing
legal problems of selling to 3rd | 05/10/2020 | 2020-10-19 | 14 days | internet, google suite, MS Teams | Blu | Ongoing
ethical problems of selling | 2020-10-05 | 2020-10-19 | 14 days | internet, google suite, MS Teams | Blu | Ongoing
reputation of selling | 2020-10-05 | 2020-10-19 | 14 days | internet, google suite, MS Teams | Blu | Ongoing
Old Equipment Practices | [5 empty] | Ongoing
Find Problems | 21/09/20 | 21/09/20 | 1 day | MS Teams, MS Word | Aidan | Completed
Look for solutions and other practices | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Aidan | Ongoing
Cost and benefits of said solutions | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Aidan | Ongoing
Conclusions/Summation of Project | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Aidan | Ongoing
Opening of new Centre |  |  |  |  | Ellis | Ongoing
Identify main issues | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Ellis | Ongoing
Research/Propose soloutions | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Ellis | Ongoing
Summarise and report findings | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite | Ellis | Ongoing
PROJECT DOCUMENTS
Project Plan | 2020-09-21 | 2020-10-05 |  | MS Excel | ALL | Ongoing | Initial plan updated with individual reseach roles and goals
Work Logbook | 2020-09-21 |  |  | MS Word | ALL | Ongoing
Introduction/Aims of project | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite |  | ALL
Findings on Security | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite |  | Robert
Findings on 3rd Party sales | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite |  | Blu
Finding on Old Equipment Practicies | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite |  | Aiden
Finding on Disability Practices | 2020-10-05 | 2020-10-19 | 14 days | MS Word, Internet, MS Teams, Google Suite |  | Ellis
Conclusions/Summation of Project | 2020-10-05 | 2020-10-14 | 9 days | MS Word, Internet, MS Teams, Google Suite | ALL | Ongoing
Bibliography | 2020-10-05 | 2020-10-14 | 9 days | MS Word, Internet, MS Teams, Google Suite | ALL | Ongoing
Completed Project | 2020-10-05 | 2020-10-14 | 9 days | MS Word, Internet, MS Teams, Google Suite | ALL | Ongoing